## Slide 1: Lecture 11
Project Management & Estimation
Mobeen Nazar
Lecturer
Software Engineering Department

## Slide 2: Objective
Resources
Metrics
Software Metrics
Project Estimation
LOC
FP
COCOMO
Summary

## Slide 3: What is Scope?
Software scope describes
  the functions and features that are to be delivered to end-users
  the data that are input and output
  the “content” that is presented to users as a consequence of using the software
  the performance, constraints, interfaces, and reliability that bound the system.
Scope is defined using one of two techniques:
A narrative description of software scope is developed after communication with all stakeholders.
A set of use-cases is developed by end-users.

## Slide 4: Resources
project
people
skills
number
locati on
reusable software
OTS
components
full-experi ence components
new components
part.-experience components
environment
hardware
software tools
network resources

## Slide 5: Problem Decomposition
Sometimes called partitioning or problem elaboration
Once scope is defined …
  It is decomposed into constituent functions
  It is decomposed into user-visible data objects
or
  It is decomposed into a set of problem classes
Decomposition process continues until all functions or problem classes have been defined
5

## Slide 6: Functional Decomposition
6
functional decomposition
Statement of
Scope
Perform a
Grammatical “parse”

## Slide 7: Metrics
Metrics are measures of quantitative assessment commonly used for comparing, and tracking performance or production.

## Slide 8: Software Metrics(con’ d)

## Slide 9: Estimation Techniques
Past (similar) project experience
Conventional estimation techniques
  task breakdown and effort estimates
  size (e.g., FP) estimates
Empirical models
Automated tools
11

## Slide 10: Size Estimation

## Slide 11: Lines of Code (LOC)
Lines of Code (LOC): As the name suggest, LOC count the total number of lines of source code in a project. The units of LOC are:
KLOC- Thousand lines of code
NLOC- Non comment lines of code
KDSI- Thousands of delivered source instruction

## Slide 12: LOC based Estimation

## Slide 13: LOC‐Based Estimation‐Example

## Slide 14: LOC‐based Estimation‐Exercise

## Slide 15: Estimation with Use-Cases
A Use-Case is a series of related interactions between a user and a system that enables the user to achieve a goal.
Use-Case Points (UCP) is a software estimation technique used to measure the software size with use cases. The concept of UCP is similar to FPs.

## Slide 17: Estimation with Use-Cases
The number of UCPs in a project is based on the following −
The number and complexity of the use cases in the system.
The number and complexity of the actors on the system.
  Various non-functional requirements (such as portability, performance, maintainability) that are not written as use cases.
  The environment in which the project will be developed (such as the language, the team’s motivation, etc.)

## Slide 20: Function Point
Function point metrics provide a standardized method for measuring the various functions of a software application.
Function point metrics, measure functionality from the users point of view, that is, on the basis of what the user requests and receives in return

## Slide 21: Function Point

## Slide 22: Types of FP Attributes

## Slide 23: FB Based Estimation Exercise

## Slide 24: FB Based Estimation Exercise
0 - No Influence
1 - Incidental
2 - Moderate
3 - Average
4 - Significant
5 - Essential

## Slide 25: FB Based Estimation Exercise
"reliable backup and recovery required ?",
"data communication required ?",
"are there distributed processing functions ?",
"is performance critical ?",
"will the system run in an existing heavily utilized operational environment ?",
"on line data entry required ?",
"does the on line data entry require the input transaction to be built over multiple screens or operations ?",
"are the master files updated on line ?",
"is the inputs, outputs, files or inquiries complex ?",
"is the internal processing complex ?",
"is the code designed to be reusable ?",
"are the conversion and installation included in the design ?",
"is the system designed for multiple installations in different organizations ?",
"is the application designed to facilitate change and ease of use by the user ?"

## Slide 26: FB Based Estimation Exercise

## Slide 27: FB Based Estimation Exercise

## Slide 28: Summary
The scope and software matric has bee learnt to estimate the project.
Different Estimation techniques help to estimate the project cost, schedule and man power effectively to produce a better product from the company end..